## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Patients Dashboard | 02.01 | Sign Up An Account | Implement Sign-Up API | 2023-10-31 | 2023-11-01 | 100% | Nikhil Bhosale
2 | Patients Dashboard | 02.01 | Sign Up An Account | Implement Core Sign-Up Logic | 2023-11-02 | 2023-11-03 | 100% | Nikhil Bhosale
3 | Patients Dashboard | 02.01 | Sign Up An Account | Create Sign-Up GUI | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale
4 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: First/Last Name are required and not null/blank | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
5 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: Street Name is required and not null/blank | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
6 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: City is required and not null/blank; String | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
7 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: Zip code is required and not null/blank (Int; length 5) | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
8 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: Email Address is required and not null/blank | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
9 | Patients Dashboard | 02.01 | Sign Up An Account | Implement validation on field: telephone number is required and not null/blank; length 11; format (1)- 1234567890 | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
10 | Patients Dashboard | 02.01 | Sign Up An Account | Implement field validation: Password/Confirm Password are required and not null/blank. | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
11 | Patients Dashboard | 02.01 | Sign Up An Account | Crosscut: FV - Field Validation -Validations of fields mentioned in previous tasks are implemented | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
12 | Patients Dashboard | 02.01 | Sign Up An Account | Crosscut: Exception Handling-Display error message if request does not process | 2023-11-03 | 2023-11-04 | 100% | Nikhil Bhosale /Kelly
13 | Patients Dashboard | 02.01 | Sign Up An Account | Analyzing database requirements | 2023-11-03 | 2023-11-04 | 100% | Kamesh
14 | Patients Dashboard | 02.01 | Sign Up An Account | Identify entities and relationships in database | 2023-11-03 | 2023-11-04 | 100% | Kamesh
15 | Patients Dashboard | 02.01 | Sign Up An Account | Arrange entities in tables, defining the primary and foreign keys | 2023-11-03 | 2023-11-04 | 100% | Kamesh
16 | Patients Dashboard | 02.01 | Sign Up An Account | Refine and normalize the data model | 2023-11-04 | 2023-11-05 | 100% | Kamesh
17 | Patients Dashboard | 02.01 | Sign Up An Account | Test Sign-Up Functionality | 2023-11-04 | 2023-11-05 | 100% | Nikhil Bhosale
18 | Patients Dashboard | 02.01 | Sign Up An Account | Execute exploratory testing | 2023-11-05 | 2023-11-08 | 40% | Team
19 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Design Doctor Profile Page | 2023-11-04 | 2023-11-05 | 100% | Nikhil Bhosale
20 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Implement API for Doctor Profiles | 2023-11-05 | 2023-11-07 | 100% | Nikhil Bhosale
21 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Implement Core Doctor Profiles Logic | 2023-11-08 | 2023-11-09 | 100% | Nikhil Bhosale
22 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Create Doctor Profile Display UI | 2023-11-09 | 2023-11-09 | 100% | Nikhil Bhosale
23 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Crosscut Error Handling: when doctor Profile is not found- Display message "No match was found" and provide options for users to perform a new search. | 2023-11-10 | 2023-11-11 | 100% | Nikhil Bhosale
25 | Patients Dashboard | 02.03 | Browse Doctors' Profiles | Execute exploratory testing | 2023-11-11 | 2023-11-15 | 80% | Team
26 | Patients Dashboard | 02.04 | Check Doctors' Availability | Design Availability Check Page | 2023-11-10 | 2023-11-10 | 100% | Nikhil Bhosale
27 | Patients Dashboard | 02.04 | Check Doctors' Availability | Implement API for Availability Check | 2023-11-10 | 2023-11-11 | 100% | Nikhil Bhosale
28 | Patients Dashboard | 02.04 | Check Doctors' Availability | Implement Core Availability Check Logic | 2023-11-10 | 2023-11-11 | 100% | Nikhil Bhosale
29 | Patients Dashboard | 02.04 | Check Doctors' Availability | Create Availability Check UI | 2023-11-10 | 2023-11-11 | 100% | Nikhil Bhosale
30 | Patients Dashboard | 02.04 | Check Doctors' Availability | Crosscut Error Handling for Unavailability: Provide error messages when a doctor's availability information cannot be retrieved. | 2023-11-10 | 2023-11-11 | 100% | Nikhil Bhosale
31 | Patients Dashboard | 02.04 | Check Doctors' Availability | Execute exploratory testing | 2023-11-10 | 2023-11-12 | 100% | Nikhil Bhosale
32 | Patients Dashboard | 02.05 | Book Appointment | Design Appointment Booking Flow | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
33 | Patients Dashboard | 02.05 | Book Appointment | Implement API for Appointment Booking | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
34 | Patients Dashboard | 02.05 | Book Appointment | Implement Core Appointment Booking Logic | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
35 | Patients Dashboard | 02.05 | Book Appointment | Create Appointment Booking UI | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
36 | Patients Dashboard | 02.05 | Book Appointment | Crosscut Data Integrity: Ensure that the appointment data is updated in real-time to reflect the changes. | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
37 | Patients Dashboard | 02.05 | Book Appointment | Crosscut error handling: Verify the availability of the selected time slot before confirming the appointment. If the slot is already unavailable, provide a error message. | 2023-11-12 | 2023-11-13 | 100% | Nikhil Bhosale
38 | Patients Dashboard | 02.05 | Book Appointment | Execute exploratory testing | 2023-11-13 | 2023-11-15 | 85% | Team

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Doctors Dashboard | 03.01 | Set Schedule Availability | Design Schedule Availability Page | 2023-11-19 | 2023-11-20 | 100% | Nikhil Bhosale
2 | Doctors Dashboard | 03.01 | Set Schedule Availability | Implement API for Setting Schedule Availability | 2023-11-20 | 2023-11-21 | 100% | Nikhil Bhosale
3 | Doctors Dashboard | 03.01 | Set Schedule Availability | Implement Core Logic for Setting Schedule Availability | 2023-11-21 | 2023-11-27 | 100% | Nikhil Bhosale
4 | Doctors Dashboard | 03.01 | Set Schedule Availability | Create UI for Setting Schedule Availability | 2023-11-27 | 2023-11-29 | 100% | Nikhil Bhosale
5 | Doctors Dashboard | 03.01 | Set Schedule Availability | Execute exploratory testing | 2023-11-29 | 2023-12-12 | 50% | Team
6 | Doctors Dashboard | 03.01 | Set Schedule Availability | S3: Acceptance Tests (Test Design, Test Cases) | 2023-11-30 | 2023-12-02 | 85% | Tiara / Vivek
7 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | S3: Acceptance Tests (Test Design, Test Cases) | 2023-11-30 | 2023-12-02 | 85% | Kamesh / Kelly
8 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | S3: Acceptance Tests (Test Design, Test Cases) | 2023-11-30 | 2023-12-02 | 85% | Mukesh/ Dhanusha/ Nikhil Kumar
9 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | Design Scheduled Appointments Page | 2023-11-29 | 2023-11-30 | 100% | Nikhil Bhosale
10 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | Implement API for Managing Scheduled Appointments | 2023-11-30 | 2023-12-01 | 100% | Nikhil Bhosale
11 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | Implement Core Logic for Managing Scheduled Appointments | 2023-12-02 | 2023-12-03 | 100% | Nikhil Bhosale
12 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | Create UI for Managing Scheduled Appointments | 2023-12-04 | 2023-12-05 | 100% | Nikhil Bhosale
13 | Doctors Dashboard | 03.02 | Manage Scheduled Appointments | Execute exploratory testing | 2023-12-05 | 2023-12-12 | 50% | Team
14 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | Design Medical Records Access Page | 2023-12-06 | 2023-12-07 | 100% | Nikhil Bhosale
15 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | Implement API for Accessing Patients' Medical Records | 2023-12-06 | 2023-12-07 | 100% | Nikhil Bhosale
16 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | Implement Core Logic for Accessing Patients' Medical Records | 2023-12-07 | 2023-12-08 | 100% | Nikhil Bhosale
17 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | Create UI for Accessing Patients' Medical Records | 2023-12-09 | 2023-12-11 | 100% | Nikhil Bhosale
18 | Doctors Dashboard | 03.03 | Access Patients' Medical Records | Execute exploratory testing | 2023-12-11 | 2023-12-12 | 20% | Team