## Road Map
PATIENT PORTAL
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/25/2023 | SPRINT2 - 11/15/2023 | SPRINT3 - 12/13/2023
01.Account Management | 01.01 Create Account | 4 | X
| 01.02 Authorize Account | 4 | X
| 01.03 Access/view Account Summary | 4 | X
| 01.04 Update Account | 4
| 01.05 Provide Customer Support | 4
02.Patient Dashboard | 02.01 Sign Up An Account | 4 |  | X
| 02.02 Update Personal Information | 3
| 02.03 Browse Doctors' Profiles | 4 |  | X
| 02.04 Check Doctors' Availability | 4 |  | X
| 02.05 Book Appointment | 4 |  | X
| 02.06 Request Virtual Consultation for Symptom Check | 4
| 02.07 Manage Health Records | 3
| 02.08 Request Prescription Refills | 2
| 02.09 Set Notification Preferences | 3
03.Doctors Dashboard | 03.01 Set Schedule Availability | 4 |  |  | X
| 03.02 Manage Scheduled Appointments | 4 |  |  | X
| 03.03 Access Patients' Medical Records | 4 |  |  | X
| 03.04 Review Lab Test Results | 4
| 03.05 Prescribe Medications | 4
| 03.06 Update Patient Records | 4
| 03.07 Conduct Telemedicine Consultations | 4
| 03.08 Generate Diagnostic Report | 3
| 03.09 Send Result Notification | 4
04.Daignostics Report | 04.01 Receive Lab Results | 3
| 04.02 View Diagnostic Reports | 3
| 04.03 Print and Download Reports | 2
05.Payment Gateway | 05.01 Process Patient Payment | 4
| 05.02 Manage Subscription Payment | 3
| 05.03 Process Advertisement Payment | 2
06.Advertising | 06.01 Add Ads | 2
| 06.02 Update Ads | 2
| 06.03 Remove Ads | 2
|  | VELOCITY: | 12 | 16 | 12